Development Phase Documentation – Dentist Front Desk

### 1. Project Overview & Business Value

- Problem solved

- Small dental front desks miss 15–40% of calls (busy, after-hours, staff occupied) → patients leave voicemail (rarely checked) or go to competitors.

- Solution value

Turns missed calls into structured digital intake summaries → team follows up same/next day → increases booked appointments without adding staff.

- Key differentiators

  - Uses existing clinic phone number (conditional forwarding)

  - AI is deliberately limited → no risk of wrong clinical/pricing answers

  - Self-serve onboarding + dentist pause control → high stickiness

- Monetization

$99/month (quarterly or annual billing), 24-hour activation delay after payment

- Compliance posture

HIPAA-eligible services only + signed BAAs + minimal PHI handling + full audit trails

### 2. High-Level Technology Stack Recap

| Layer | Technology | Primary Responsibility |
| --- | --- | --- |
| Backend & Logic | FastAPI (Python 3.11+) | API, WebSocket proxy (Twilio ↔ OpenAI), business logic |
| Telephony / OTP | Twilio | Call receiving, forwarding target, phone verification |
| Voice Conversation AI | OpenAI Realtime API | Natural speech-to-speech conversation (strict prompt) |
| Database | PostgreSQL + SQLAlchemy | Clinic configs, consents, intake records, audits |
| Frontend | Next.js 15 (React + TypeScript) | Onboarding wizard + dentist dashboard |
| Payments | Stripe | Subscriptions + delayed activation |
| Hosting | AWS (HIPAA-eligible region) | Backend, DB, secure WebSocket traffic |
| Calendar Integration | Google Calendar API / Microsoft Graph API / Apple CalDAV | Live availability lookup mid-call + dentist-confirmed booking write-back |
| Auth | Clerk + Twilio Verify | Dentist login + phone ownership proof |

### 3. Development Phases – Timeline & Deliverables

| Phase | Key Activities & Deliverables | Success Criteria / Milestones | Dependencies / Risks |
| --- | --- | --- | --- |
| Phase 1 – Core Voice Engine | - Build FastAPI WebSocket proxy (Twilio Media Streams ↔ OpenAI Realtime) - Implement conservative conversation flow (greet → reason → name/ID → ack → end) - Parse & structure summary output - Basic transcript + reason storage in Postgres | - End-to-end test call → clean intake JSON saved in DB - AI never attempts booking/clinical answer (guardrail test suite passes) - Latency < 1.5s average | - Twilio + OpenAI Python example repo must work out-of-box - Audio quality / interruption handling bugs |
| Phase 2 – Delivery Layer | - E.164 number normalization - Email + dashboard push of intake summary - Carrier-specific forwarding instruction docs | - Missed call simulation → intake appears in test dashboard - Email delivery confirmed | - Carrier forwarding quirks (need real mobile/landline tests) |
| Phase 3 – Self-Serve Onboarding Flow | - 5-screen Next.js wizard: 1. Google Business Profile link → auto-fill 2. Twilio Verify OTP to clinic phone 3. Consent checkboxes + terms links 4. Call activation toggles (busy/unanswered/after-hours) 5. Stripe checkout + 24h delay logic - Multi-tenant DB isolation per clinic | - New test clinic can complete onboarding in <10 min - Phone ownership verified - Payment succeeds → config saved | - Google API rate limits / parsing changes - Stripe webhook reliability |
| Phase 3.5 – Calendar-Based Appointment Booking | - Calendar OAuth connection step added to onboarding wizard (Google Calendar / Outlook / Apple CalDAV) - AI checks live calendar availability mid-call via API - AI proposes available slot to patient and collects verbal confirmation - Booking created as “Pending Confirmation” in DB (not auto-confirmed) - Dentist notified via dashboard of pending booking request - Dentist approves, reschedules, or declines from dashboard - Confirmed booking written back to calendar via API - AI restricted to predefined appointment types only (cleaning, checkup, emergency, etc.) | - Dentist can connect calendar, view pending bookings, and approve/decline from dashboard - End-to-end booking flow tested: call → slot proposal → pending → dentist approval → calendar updated - AI guardrails confirmed: no auto-booking, no clinical decisions | - Google Calendar / Outlook OAuth approval required - Dental-specific software (Dentrix, Eaglesoft) has no open API – out of scope - Calendar API latency may add ~1–2s to call response time - Double-booking risk if calendar sync is delayed – optimistic locking required |
| Phase 4 – Dentist Dashboard & Control | - Login (Clerk) - List of intake records (search/filter by date/reason) - Pause / resume system toggle - Audit log export (CSV/PDF) - Basic usage stats (calls caught today/week, call history, call recordings.) - Calling interface within the system. - Live call monitoring. | - Dentist can view real intakes & pause system - Pause immediately stops forwarding handling | - UI/UX feedback loop needed early |
| Phase 5 – Security, Compliance Hardening & Testing | - Encryption at rest/transit - Role-based access + minimal PHI - Full audit trail implementation - Penetration testing (healthcare scenarios) - End-to-end carrier tests (Verizon, AT&T, Rogers, etc.) - Beta onboarding with 3–5 real dental clinics | - Zero critical/high vulnerabilities - Beta clinics report smooth setup & value - First compliance self-audit passed | - Beta clinic recruitment & real PHI handling caution - Pen-test findings requiring fixes |

### 4. Handling multi-tenancy

For multi-tenancy we will have a shared database and seperate PostgresSQL DB schema for each tenant. Tenant identification will be based on unique tenant_ID & schema_name. Implementation of a proper RBAC system.


5. Costing

Monthly cost breakdown — 300 calls for llm

| Component | OpenAI gpt-realtime | OpenAI gpt-mini-realtime | Gemini 2.5 Flash Live |
| --- | --- | --- | --- |
| Audio in (patient speech) | $7.13 @ $32/M tok | $2.25 @ $10/M tok | $0.56 @ $1.00/M tok |
| Audio out (AI speech) | $14.40 @ $64/M tok | $4.50 @ $20/M tok | $1.41 @ $2.50/M tok |
| Text in (system prompt) | $0.96 @ $4/M | $0.14 @ $0.60/M | $0.07 @ $0.30/M |
| Text out (transcript) | $0.91 @ $16/M | $0.14 @ $2.40/M | $0.14 @ $2.50/M |
| Monthly total | $23.40 | $7.03 | $2.18 |

Monthly cost breakdown — 300 calls Twilio

| Component | Monthly Cost |  |  |
| --- | --- | --- | --- |
| Voice (Inbound + Outbound) | $16.88 |  |  |
| Phone number rental | $1.00 |  |  |
| Total per clinic per month | $17.88 |  |  |

6. Why Twilio or such services are needed?

- Receiving the forwarded call — when the clinic's phone is busy/unanswered, it forwards to a Twilio number

- Twilio Media Streams — this is the critical piece that streams the live call audio over WebSocket to your FastAPI backend, which then pipes it into OpenAI's/Gemini  Realtime API for the AI conversation

- Without this, the AI can't hear or speak on the call at all